## Sheet1
Project Plan [Jan 30 – April 30 2015]
No | Content | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
System Analysis
1 | Requirement Analysis | 1. Functional Requirement
2. Page by Page Fucntionality
3. Functional Description
2 | Development Method | 1. Decide Development Method
2. Install Eclipse, Tomcat, Mysql
3 | High Level Architecture | 1. Construct System Architecture
2. Draw High Level Architecture
4 | Complete Design Document | 1. Use Case Diagram
2. Class Diagram
3. Sequence Diagram
4. Database Design
5. Information Architecture
6. GUI prototype
5 | Make Project Plan Document | 1. Draw Gant Chart
2. Set Milestones
Implement
6 | Create Prototype of Program | 1. Implement web page with simple functions
7 | Implement System | 1. Implement Server
2. Implement Database
3. Implement Web pages
8 | Implement functions | 1. Implement Administrator’s functions
2. Implement Receptionist’s functions
3. Implement User’s functions
9 | Implement UI Design | 1. Implement CSS
2. Enhance UI Design
Testing and Bug Fixing
10 | Testing | 1. Testing All Functions
2. Testing CSS Design
3. Make Testing List
11 | Bug Fixing | 1. Make Bug Lists
| and | 2. Fix Bugs and Retest
| Enhancement | 3. Enhance a few UI Design and Functions
12 | Retest and Release | 1. Retest Bugs in Fixed Lists
2. Complete Final Report and Presentation
3. Demonstrate Program
Note on I2: Oulu Winter Break
Note on L2: Dublin Easter Break